## Instructions
empeo Registration — Automation Test Report (Gofive · Automate Tester Exam 1.0)
Candidate: Newyear (Yatichapat Kanta) · Role: Automate QA Engineer (Gofive online assessment, part 6) · 27 Oct 2026
How this workbook is organized
• | Test Plan & Summary — project info, scope, test data, and an auto-calculated Pass/Fail dashboard per module (do not edit the dashboard formulas).
• | Test Cases — one flat, filterable table: 24 scenarios across 5 modules (Registration form, OTP verification, Promo code, Validation / error handling, Edge cases – phone), one row per step.
• | Bug Report — 6 findings observed on UAT (UX gaps, items that need PO confirmation, and an intermittent slow redirect), each with steps, evidence and the related test case.
• | Picture - Evidence — every screenshot with a preview and a link (GitHub repo docs/), plus links to the videos and the HTML report.
How the Test Cases were executed
• | All scenarios were executed automatically with Playwright Test (JavaScript) on https://portal.uat.gofive.co.th/Register/empeo; each Scenario ID is also the automated test title, e.g. "TC-OTP-02 …".
• | Pass / Fail is filled ONLY on the LAST step row of each Scenario ID — this is what the Summary dashboard counts. Earlier steps show 'As expected' in Actual Result.
• | Pass / Fail comes from the final full run on the tester's machine (Windows 11, Chromium). Run history is in Test Plan & Summary.
• | 'Evidence' links open the screenshot on GitHub; the Remark column names the spec file › test, so the same case can be found in the HTML report.
• | Data-driven cases (e.g. TC-VAL-02 ×5, TC-PRM-02 ×3) are one scenario here but several automated runs: 24 scenarios = 35 automated runs.
How bugs are logged
• | Every finding gets one row in Bug Report; none of the 35 automated checks fail on the final run, so the findings are UX / requirement / environment observations, not failed assertions.
• | 'Related Test Case' links back to the Scenario ID (e.g. 'TC-VAL-05') that shows the behaviour.
• | Status: 'Open' = behaviour to fix; 'Need clarification' = rule not defined in the brief (ask PO); 'Observed (intermittent)' = UAT timing issue.
• | 'Picture / Evidence' is a clickable link to the screenshot (GitHub) — same files as the Drive folder 'Evident Photo'.
Color legend
• | Orange header = sheet header row.
• | Grey rows = alternate scenarios (readability only).
• | Green / Red in Pass-Fail cells = conditional formatting, updates automatically.
Links
•
•
•
•
•
Test environment reference
• | Register page: https://portal.uat.gofive.co.th/Register/empeo (UAT, Thai UI)
• | Fixed test data from the brief: phone 0967690708 · OTP 123456 · promo code FREE15DAY
• | Other data is generated per test: unique company name + unique e-mail domain (the system allows one account per e-mail domain).
• | Run locally: npm ci → npx playwright install chromium → npx playwright test → npx playwright show-report

## Test Plan & Summary
Test Plan & Summary
Project Name | empeo – Free-trial Registration
Document Name | Test Scripts – Automation Tester Exam 1.0
Candidate / Tester | Newyear (Yatichapat Kanta)
Role | Automation Tester
Created | 27/10/2026
Environment | UAT https://portal.uat.gofive.co.th/Register/empeo · Windows 11 · Chromium (Playwright 1.64.1) · TH locale
Test Data | Phone 0967690708 · OTP 123456 · Promo FREE15DAY · other data generated per test (unique company + e-mail domain)
Scope | Successful registration, OTP verification, promo code validation, required fields & error handling, edge cases (invalid phone, expired OTP, reused promo)
Out of scope | Thai-company (tax ID lookup) path; real OTP expiry time; SMS delivery
Automation | Playwright Test 1.64 (JavaScript), POM + fixtures, 24 cases / 35 automated runs
Dashboard
Module | Total Test Cases | Pass | Fail | Blocked | N/A | Not Executed | % Complete | % Pass Rate
Registration form
OTP verification
Promo code
Validation / error handling
Edge cases – phone
Total
Run history (27/10/2026)
15:59 npx playwright test (4 workers) – 35 passed / 0 failed, 2.2 min
16:08 npm run test:video (video + trace for every test) – 35 passed / 0 failed, 4.0 min
16:47 npx playwright test (tester's run) – 33 passed / 2 failed: TC-OTP-01, TC-OTP-03 (redirect after OTP took > 10 s on UAT → BUG-06)
Fix: wait for set-password page up to 30 s, dropdown/checkbox clicks retried, 1 retry on UAT (retries are reported as "flaky", not hidden)
17:13 FINAL – npx playwright test (2 workers, 1 retry) – 35 passed / 0 failed / 0 flaky, 3.0 min ← result used in Test Cases

## Test Cases
Module | Scenario ID | Type | Scenario | Step No | Function | Condition / Procedure | Checking | Expected Result | Actual Result | Pass / Fail | Evidence (Screenshot) | Tester | Test Date | Remark (automated test)
Registration form | TC-REG-01 | Normal case | Register with valid data + promo FREE15DAY, verify OTP, set password | 01.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Registration form | TC-REG-01 | Normal case |  | 01.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
Registration form | TC-REG-01 | Normal case |  | 01.3 | Promo code | Click "ใช้โค้ดส่วนลด", enter FREE15DAY, click "ใช้โค้ด" | Fields for filling / button | Code shown as applied "FREE15DAY" | As expected
Registration form | TC-REG-01 | Normal case |  | 01.4 | Submit | Click "ทดลองใช้ฟรี" | Redirect Screen | OTP dialog shows "…ส่งไปยัง 096-XXX-0708" and ref number; POST /api/v2/register has couponCode FREE15DAY | As expected
Registration form | TC-REG-01 | Normal case |  | 01.5 | Verify OTP | Enter 123456, click "ยืนยัน" | Redirect Screen | Redirect to /Register/empeo/create-password?token=… | As expected
Registration form | TC-REG-01 | Normal case |  | 01.6 | Set password | Enter QaAuto12345 in both fields, click "ตั้งรหัสผ่าน" | Redirect Screen | "empeo พร้อมใช้งานแล้ว!" and button "เริ่มต้นใช้งาน" shown | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | registration.spec.js › TC-REG-01
Registration form | TC-REG-02 | Normal case | Register without promo code (optional field) | 02.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Registration form | TC-REG-02 | Normal case |  | 02.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
Registration form | TC-REG-02 | Normal case |  | 02.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
Registration form | TC-REG-02 | Normal case |  | 02.4 | Verify button | Do not type OTP | button | "ยืนยัน" is disabled | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | registration.spec.js › TC-REG-02
Registration form | TC-REG-03 | Error case | Set-password rules (case, digit, 8+ chars, confirmation match) | 03.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Registration form | TC-REG-03 | Error case |  | 03.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
Registration form | TC-REG-03 | Error case |  | 03.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
Registration form | TC-REG-03 | Error case |  | 03.4 | Verify OTP | Enter 123456, click "ยืนยัน" | Redirect Screen | Set-password page "กรุณาตั้งรหัสผ่าน" | As expected
Registration form | TC-REG-03 | Error case |  | 03.5 | Weak password | Enter abc / abcdefgh / ABCDEFGH1 / Abcdefgh / Ab1 in both fields | button | "ตั้งรหัสผ่าน" disabled for each | As expected
Registration form | TC-REG-03 | Error case |  | 03.6 | Mismatch | Password QaAuto12345, confirm QaAuto12345x, click "ตั้งรหัสผ่าน" | Message / Redirect Screen | "รหัสผ่านไม่ตรงกัน" shown; stays on set-password page | As expected
Registration form | TC-REG-03 | Error case |  | 03.7 | Valid password | QaAuto12345 in both fields | button | "ตั้งรหัสผ่าน" enabled | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | registration.spec.js › TC-REG-03
OTP verification | TC-OTP-01 | Normal case | Correct OTP 123456 | 01.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
OTP verification | TC-OTP-01 | Normal case |  | 01.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
OTP verification | TC-OTP-01 | Normal case |  | 01.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
OTP verification | TC-OTP-01 | Normal case |  | 01.4 | Verify OTP | Enter 123456, click "ยืนยัน" | Redirect Screen | Redirect to set-password page | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | otp.spec.js › TC-OTP-01 · Failed once in run 16:47 (redirect after OTP > 10 s on UAT, see BUG-06); passed after wait 30 s + 1 retry
OTP verification | TC-OTP-02 | Error case | Wrong OTP | 02.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
OTP verification | TC-OTP-02 | Error case |  | 02.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
OTP verification | TC-OTP-02 | Error case |  | 02.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
OTP verification | TC-OTP-02 | Error case |  | 02.4 | Verify OTP | Enter 000000, click "ยืนยัน" | Message | Toast "OTP ไม่ถูกต้อง กรุณาลองใหม่อีกครั้ง"; dialog stays; OTP boxes cleared | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | otp.spec.js › TC-OTP-02
OTP verification | TC-OTP-03 | Normal case | Retry with correct OTP after a wrong one | 03.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
OTP verification | TC-OTP-03 | Normal case |  | 03.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
OTP verification | TC-OTP-03 | Normal case |  | 03.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
OTP verification | TC-OTP-03 | Normal case |  | 03.4 | Wrong OTP | Enter 111111, click "ยืนยัน" | Message | Wrong-OTP toast | As expected
OTP verification | TC-OTP-03 | Normal case |  | 03.5 | Correct OTP | Enter 123456, click "ยืนยัน" | Redirect Screen | Redirect to set-password page | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | otp.spec.js › TC-OTP-03 · Failed once in run 16:47 (redirect after OTP > 10 s on UAT, see BUG-06); passed after wait 30 s + 1 retry
OTP verification | TC-OTP-04 | Error case | Verify button needs all 6 digits | 04.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
OTP verification | TC-OTP-04 | Error case |  | 04.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
OTP verification | TC-OTP-04 | Error case |  | 04.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
OTP verification | TC-OTP-04 | Error case |  | 04.4 | Partial OTP | Type 12345 | button | "ยืนยัน" disabled | As expected
OTP verification | TC-OTP-04 | Error case |  | 04.5 | Full OTP | Type 6 (6th digit) | button | "ยืนยัน" enabled | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | otp.spec.js › TC-OTP-04
OTP verification | TC-OTP-05 | Edge case | OTP accepts digits only | 05.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
OTP verification | TC-OTP-05 | Edge case |  | 05.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
OTP verification | TC-OTP-05 | Edge case |  | 05.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
OTP verification | TC-OTP-05 | Edge case |  | 05.4 | Non-digits | Type ab!@cd | Fields for filling | Boxes stay empty; "ยืนยัน" disabled | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | otp.spec.js › TC-OTP-05
OTP verification | TC-OTP-06 | Normal case | Resend OTP after 30-second countdown | 06.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
OTP verification | TC-OTP-06 | Normal case |  | 06.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
OTP verification | TC-OTP-06 | Normal case |  | 06.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
OTP verification | TC-OTP-06 | Normal case |  | 06.4 | Countdown | Observe resend area | Message | "รับ OTP ใหม่อีกครั้งได้ใน 0:30", no resend link | As expected
OTP verification | TC-OTP-06 | Normal case |  | 06.5 | Resend | Wait until countdown ends, click "ส่งใหม่อีกครั้ง" | Link / Message | New ref number; countdown restarts | As expected
OTP verification | TC-OTP-06 | Normal case |  | 06.6 | Verify OTP | Enter 123456, click "ยืนยัน" | Redirect Screen | Redirect to set-password page | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | otp.spec.js › TC-OTP-06
OTP verification | TC-OTP-07 | Edge case | Expired OTP (server response simulated) | 07.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
OTP verification | TC-OTP-07 | Edge case |  | 07.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
OTP verification | TC-OTP-07 | Edge case |  | 07.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
OTP verification | TC-OTP-07 | Edge case |  | 07.4 | Simulate expiry | verify-otp returns business error (code 4001) | - | Mock active | As expected
OTP verification | TC-OTP-07 | Edge case |  | 07.5 | Verify OTP | Enter 123456, click "ยืนยัน" | Message / Redirect Screen | Error toast shown; no redirect | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | otp.spec.js › TC-OTP-07
OTP verification | TC-OTP-08 | Normal case | Close OTP dialog keeps form data | 08.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
OTP verification | TC-OTP-08 | Normal case |  | 08.2 | Fill form | Select "อื่นๆ"; company name (unique); business type "เทคโนโลยี"; users "1-20"; unique e-mail; first/last name; phone 0967690708; tick consent | Fields for filling | All fields accept the values, no error | As expected
OTP verification | TC-OTP-08 | Normal case |  | 08.3 | Submit | Click "ทดลองใช้ฟรี" | Button / Redirect Screen | OTP dialog "กรุณาตรวจสอบข้อความ" with 6 OTP boxes is shown | As expected
OTP verification | TC-OTP-08 | Normal case |  | 08.4 | Close | Click X on the dialog | Redirect Screen / Fields | Dialog closed; e-mail and phone still filled | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | otp.spec.js › TC-OTP-08
Promo code | TC-PRM-01 | Normal case | Valid promo FREE15DAY | 01.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Promo code | TC-PRM-01 | Normal case |  | 01.2 | Promo code | Click "ใช้โค้ดส่วนลด", enter FREE15DAY, click "ใช้โค้ด" | button / API | coupon-validation 200, isValid=true; code shown as applied; input hidden | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | promo.spec.js › TC-PRM-01
Promo code | TC-PRM-02 | Error case | Invalid promo (INVALID999, FREE15DAYX, 12345) | 02.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Promo code | TC-PRM-02 | Error case |  | 02.2 | Promo code | Apply each invalid code | Message | "คูปองโค้ดไม่ถูกต้อง"; code not applied | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | promo.spec.js › TC-PRM-02 (x3)
Promo code | TC-PRM-03 | Normal case | Correct an invalid code to a valid one | 03.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Promo code | TC-PRM-03 | Normal case |  | 03.2 | Invalid code | Apply WRONGCODE | Message | "คูปองโค้ดไม่ถูกต้อง" | As expected
Promo code | TC-PRM-03 | Normal case |  | 03.3 | Valid code | Apply FREE15DAY | Message | Error gone; FREE15DAY applied | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | promo.spec.js › TC-PRM-03
Promo code | TC-PRM-04 | Edge case | Reused promo code (FREE15DAY in a second registration) | 04.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Promo code | TC-PRM-04 | Edge case |  | 04.2 | First use | Apply FREE15DAY | Message | Applied | As expected
Promo code | TC-PRM-04 | Edge case |  | 04.3 | Second use | New browser session, open page, apply FREE15DAY | Message | Applied again (multi-use code) – see BUG-04 | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | promo.spec.js › TC-PRM-04
Validation / error handling | TC-VAL-01 | Error case | Submit empty form | 01.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Validation / error handling | TC-VAL-01 | Error case |  | 01.2 | Submit | Click "ทดลองใช้ฟรี" with nothing filled | Message | "กรุณากรอกประเภทธุรกิจ", "กรุณากรอกผู้ใช้งาน", "กรุณากรอกอีเมล", "กรุณากรอกชื่อ", "กรุณากรอกนามสกุล"; no register request | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | validation.spec.js › TC-VAL-01
Validation / error handling | TC-VAL-02 | Error case | One required field missing (email / first name / last name / business type / users) | 02.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Validation / error handling | TC-VAL-02 | Error case |  | 02.2 | Fill form | Fill all fields except one, tick consent | Fields for filling | - | As expected
Validation / error handling | TC-VAL-02 | Error case |  | 02.3 | Submit | Click "ทดลองใช้ฟรี" | Message | Required message for that field; no register request | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | validation.spec.js › TC-VAL-02 (x5)
Validation / error handling | TC-VAL-03 | Error case | Invalid e-mail format (not-an-email, qa@, @qa-test.co.th, qa@qa-test) | 03.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Validation / error handling | TC-VAL-03 | Error case |  | 03.2 | Fill form | Valid data with the invalid e-mail | Fields for filling | - | As expected
Validation / error handling | TC-VAL-03 | Error case |  | 03.3 | Submit | Click "ทดลองใช้ฟรี" | Message | "กรุณาใส่อีเมลที่ถูกต้อง" | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | validation.spec.js › TC-VAL-03 (x4)
Validation / error handling | TC-VAL-04 | Error case | E-mail domain already registered (example.com) | 04.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Validation / error handling | TC-VAL-04 | Error case |  | 04.2 | Fill form | Valid data, e-mail qa.<n>@example.com | Fields for filling | - | As expected
Validation / error handling | TC-VAL-04 | Error case |  | 04.3 | Submit | Click "ทดลองใช้ฟรี" | Message | "โดเมนนี้มีบัญชีใช้งานแล้ว"; no register request | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | validation.spec.js › TC-VAL-04
Validation / error handling | TC-VAL-05 | Error case | Consent not ticked | 05.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Validation / error handling | TC-VAL-05 | Error case |  | 05.2 | Fill form | Valid data, consent NOT ticked | Fields for filling | - | As expected
Validation / error handling | TC-VAL-05 | Error case |  | 05.3 | Submit | Click "ทดลองใช้ฟรี" | Redirect Screen / API | OTP dialog not opened; no register request (no message shown – BUG-01) | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | validation.spec.js › TC-VAL-05
Edge cases – phone | TC-EDGE-01 | Edge case | Invalid phone (12345, 096769070, 09676907089) | 01.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Edge cases – phone | TC-EDGE-01 | Edge case |  | 01.2 | Fill form | Valid data with the invalid phone | Fields for filling | - | As expected
Edge cases – phone | TC-EDGE-01 | Edge case |  | 01.3 | Submit | Click "ทดลองใช้ฟรี" | Message | "รูปแบบเบอร์โทรศัพท์ไม่ถูกต้อง"; no OTP dialog | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | phone.edge.spec.js › TC-EDGE-01 (x3)
Edge cases – phone | TC-EDGE-02 | Edge case | Letters in phone field | 02.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Edge cases – phone | TC-EDGE-02 | Edge case |  | 02.2 | Phone | Type abcXYZ | Fields for filling | Field stays empty | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | phone.edge.spec.js › TC-EDGE-02
Edge cases – phone | TC-EDGE-03 | Edge case | Phone max length | 03.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Edge cases – phone | TC-EDGE-03 | Edge case |  | 03.2 | Phone | Type 20 digits | Fields for filling | Only 15 characters kept | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | phone.edge.spec.js › TC-EDGE-03
Edge cases – phone | TC-EDGE-04 | Error case | Phone empty | 04.1 | Open page | Open /Register/empeo | Redirect Screen | Registration form "ทดลองใช้งาน empeo ฟรี!" is shown | As expected
Edge cases – phone | TC-EDGE-04 | Error case |  | 04.2 | Fill form | Valid data, phone empty | Fields for filling | - | As expected
Edge cases – phone | TC-EDGE-04 | Error case |  | 04.3 | Submit | Click "ทดลองใช้ฟรี" | Redirect Screen | OTP dialog not opened | As expected | Pass |  | Newyear (Yatichapat Kanta) | 27/10/2026 | phone.edge.spec.js › TC-EDGE-04

## Bug Report
Incident No. | Occurred Date | Screen | Related Test Case | Raised by | Checked by | Priority | Severity | Status | Detail (Description) | Steps to Reproduce | Expected Result | Actual Result | Picture / Evidence | Environment | Major Class | Minor Class | Remark
BUG-01 | 27/10/2026 | Registration form | TC-VAL-05 | Newyear (Yatichapat Kanta) |  | Medium | Minor | Open | Submitting without ticking the consent box does nothing and shows no message, so the user does not know why. | 1. Open /Register/empeo 2. Fill all fields with valid data 3. Leave consent unticked 4. Click "ทดลองใช้ฟรี" | A message asks the user to accept the policy/terms (or the button is disabled) | Nothing happens; no message |  | UAT · Chromium · TH | UX | Validation message
BUG-02 | 27/10/2026 | Set password | TC-REG-03 | Newyear (Yatichapat Kanta) |  | Low | Minor | Open | When confirmation does not match, "ตั้งรหัสผ่าน" stays enabled, while other rule failures disable it (inconsistent). | 1. Reach set-password page 2. Password QaAuto12345, confirm QaAuto12345x | Button disabled like other rule failures | Button enabled; only inline "รหัสผ่านไม่ตรงกัน"; click does nothing |  | UAT · Chromium · TH | UX | Consistency
BUG-03 | 27/10/2026 | Registration form | TC-EDGE-01/02/03 | Newyear (Yatichapat Kanta) |  | Low | Trivial | Open | Phone field accepts "-" and up to 15 characters; format error only on submit. | 1. Type "-" or 15 digits in phone | Only digits; length fits the selected country | "-" accepted; 15 chars accepted |  | UAT · Chromium · TH | Validation | Input mask
BUG-04 | 27/10/2026 | Promo code | TC-PRM-04 | Newyear (Yatichapat Kanta) |  | Low | Info | Need clarification | FREE15DAY is multi-use (usageCount > 3,000, isLock=false). Expected rule for a "reused promo code" is unclear. | 1. Apply FREE15DAY in two sessions | Per business rule (confirm with PO) | Accepted both times |  | UAT · Chromium · TH | Requirement | Clarification
BUG-05 | 27/10/2026 | Registration API | TC-REG-01 | Newyear (Yatichapat Kanta) |  | Low | Info | Need clarification | Same phone number can register many companies; no duplicate-phone block (duplicateInfo returns isDuplicate=false). | 1. Register twice with phone 0967690708 | Per business rule (confirm with PO) | Both registrations reach OTP |  | UAT · Chromium · TH | Requirement | Clarification
BUG-06 | 27/10/2026 | OTP → Set password | TC-OTP-01, TC-OTP-03 | Newyear (Yatichapat Kanta) |  | Low | Minor | Observed (intermittent) | After a correct OTP, the redirect to the set-password page sometimes takes more than 10 s on UAT. In the local run at 16:47, 2 of 35 tests failed on the 10 s wait although the page did open afterwards (see screenshot in the report). | 1. Submit valid form 2. Enter OTP 123456 → ยืนยัน 3. Measure time until /create-password opens | Set-password page opens within a few seconds | Took > 10 s in 2 runs (UAT under load). Test wait raised to 30 s + 1 retry; reruns pass |  | UAT · Chromium · TH | Performance | Environment / UAT

## Picture - Evidence
# | File (repo docs/) | What it shows | Link | Preview
1 | 01-register-form.png | Registration form (default state)
2 | 02-empty-submit.png | Required-field messages (TC-VAL-01)
3 | 08-promo-opened.png | Promo field opened
4 | 09-promo-invalid.png | Invalid promo message (TC-PRM-02)
5 | 10-promo-valid.png | FREE15DAY applied (TC-PRM-01)
6 | 11-otp-page.png | OTP dialog (TC-REG-01)
7 | 12-no-consent.png | Consent not ticked – nothing happens (BUG-01)
8 | 13-otp-wrong.png | Wrong OTP toast (TC-OTP-02)
9 | 14-otp-correct-filled.png | OTP 123456 entered
10 | 15-success.png | Set-password page after correct OTP
11 | 16-phone-invalid.png | Invalid phone message (TC-EDGE-01)
12 | 17-create-password.png | Set-password page
13 | 19-after-password.png | "empeo พร้อมใช้งานแล้ว!" success screen
14 | 20-email-invalid.png | Invalid e-mail message (TC-VAL-03)
15 | 21-email-dup-domain.png | Duplicate domain message (TC-VAL-04)
16 | 22-otp-resent.png | OTP resent, new ref (TC-OTP-06)
17 | 23-password-mismatch.png | Password mismatch (BUG-02)
18 | report/01-html-report-summary.jpg | HTML report – 35/35 passed (video run 16:08)
19 | report/02-tc-reg-01-steps.jpg | HTML report – TC-REG-01 steps, final screenshot, trace and video
20 | report/03-local-run-1647-otp01-failed.jpg | HTML report – run 16:47, TC-OTP-01 failed on 10 s wait; page did open (BUG-06)
21 | submission/00-submission-card.jpg | Submission card (summary + links)
Videos and folders
Headed run, screen recording (Drive / Video)
Playwright recording of all 35 tests, 8 min (GitHub)
Drive folder (workbook, Evident Photo, Video)
GitHub repository